## Overview
GradProcess AI — Project Status
AI graduate-scheme preparation platform · status as at 21 July 2026
CURRENT STAGE
Stage 4 of 6 — Infrastructure & Deployment
Product code is complete and audited. Deployment is queued behind two user actions: GitHub push authentication and recreating the Supabase project.
STAGE TRACKER
1. Concept & spec | COMPLETE
2. Product build (14 modules, 23 pages) | COMPLETE
3. Security & readiness audit | COMPLETE
4. Infrastructure & deployment | IN PROGRESS
5. Accounts, data persistence & payments | NOT STARTED
6. Public launch | NOT STARTED
SUMMARY COUNTS
Completed work items
Outstanding work items
— of which blocked on you (Nassim)
Open blockers / risks
— of which Critical severity
Automated tests passing | 28
TypeScript errors | 0
YOUR IMMEDIATE NEXT STEPS (in order)
1. Fix GitHub authentication (personal access token with 'repo' scope) and push the 2 waiting commits.
2. Create a new Supabase project at supabase.com and run supabase/schema.sql in its SQL editor (~10 min).
3. Send the 3 new Supabase keys for .env.local, and add them to Vercel project settings.
4. Rotate the Anthropic API key at console.anthropic.com (old prefix was publicly exposed).
5. Verify the Vercel deployment together — then move to Stage 5.

## Completed Work
Item | Area | Description | Evidence / verification | Status
Marketing site (7+ pages) | Frontend | Cinematic dark landing with hero video, features, pricing, 13 sector pages, privacy, terms, AI disclosure. | All pages return HTTP 200; visually toured in browser. | Done
Authentication UI | Frontend | Login, signup (5-requirement password meter), forgot password, verify email, 7-step onboarding. | Pages render; password scoring unit-tested (28-test suite). | Done
Dashboard — Readiness Command Centre | Frontend | Animated readiness ring, XP/streak/level gamification, module grid, daily challenges, company readiness. | Browser E2E: scores update live (STAR 62 flowed to global readiness). | Done
CV Tailoring & ATS scoring | AI module | PDF/DOCX/TXT upload, Claude-powered ATS analysis: keyword gaps, rewritten bullets, tailored summary. | parse-cv round-trip tested; .exe upload correctly rejected. | Done
STAR Answer Builder | AI module | 23 competencies, experience bank, AI-scored STAR answers with 60s/90s/2min versions. | Live AI call verified: generated & scored answer 62/100. | Done
AI Video Interview Simulator | AI module | Webcam recording, playback, transcript download, live filler-word detection, AI scoring across 6 modes. | Filler-word engine unit-tested (word boundaries, severity tiers). | Done
Psychometric Tests | AI module | Numerical / verbal / logical / abstract, AI-generated timed questions with worked explanations. | Live API test returned real questions with correct answers. | Done
Industry Hub | Content | 13 sectors, live RSS news aggregation (FT, Economist, BBC...), AI sector insights. | News API returned live April-2026 articles in test. | Done
Application Tracker | Frontend | Kanban pipeline, deadlines, AI role breakdown, stage history. | Page renders with stats bar and empty state; add-flow present. | Done
Full Process Exam (demo) | Frontend | 9-stage end-to-end recruitment simulation with report. | Renders and completes in demo mode (mock scores — see Outstanding). | Done
Reports & Settings | Frontend | Analytics charts (radar, trends), profile/security/privacy settings, data export, account deletion. | Pages return 200; export API correctly returns 401 unauthenticated. | Done
Ava AI Coach | AI module | Floating contextual AI coach on every page. | Live API test: correct conversational answer returned. | Done
13 AI API routes (Claude) | Backend | All AI features server-side via Anthropic claude-sonnet-4-6; JSON outputs; API key never client-side. | Key confirmed server-only in all 14 usages; 3 routes live-tested. | Done
Stripe integration (code) | Payments | Checkout, customer portal, signature-verified webhook; £19.99/mo Student Pro plan. | Code review + webhook↔schema consistency now regression-tested. | Done
Supabase schema with RLS | Database | 13 tables (profiles, subscriptions, CVs, applications, interviews, psychometrics, audit logs...) — every table row-level-secured. | Schema corrected in audit; consistency tests pass. | Done
Security hardening | Security | CSP + security headers, file-upload blocklist, input validation (Zod) on API routes, webhook signature checks. | Headers in next.config; malicious upload rejected in live test. | Done
Dev environment on new laptop | DevOps | Node.js install, dependency reinstall for Apple Silicon, dev server running. | App runs locally; AI calls succeed. | Done
Full security & readiness audit | Audit | 6 confirmed defects found and fixed (incl. production API-key leak, broken Stripe webhook writes). | AUDIT-REPORT.md in repo; all fixes regression-tested. | Done
Automated test suite | Quality | Vitest: 28 tests — validation, filler-words, webhook↔schema drift guard. npm test / npm run typecheck. | 28/28 passing; TypeScript 0 errors with build enforcement ON. | Done
Fixes committed to git | DevOps | 2 clean commits on local main ready to push (feature work + audit fixes). | git log: 33e15b6, b21a291; working tree clean. | Done

## Outstanding Work
Item | Area | Priority | Effort | Owner | Depends on | Notes
Push commits to GitHub | DevOps | Critical | 5 min | Nassim | Valid GitHub token | Blocked on authentication — needs a personal access token with 'repo' scope (or GitHub CLI login). Unblocks the Vercel deploy that removes the live API-key leak.
Create new Supabase project + run schema | Database | Critical | 10 min | Nassim | — | Old project is deleted (DNS NXDOMAIN). Create at supabase.com, paste supabase/schema.sql into SQL Editor, run once.
Update Supabase keys locally + in Vercel | DevOps | Critical | 10 min | Nassim | New Supabase project | URL, anon key, service-role key into .env.local and Vercel → Settings → Environment Variables.
Rotate Anthropic API key | Security | High | 5 min | Nassim | — | Old key's prefix was publicly exposed via the (now deleted) /api/debug route. Rotate at console.anthropic.com, update .env.local + Vercel.
Verify production deployment | DevOps | High | 30 min | Claude | Push + Supabase + keys | Confirm deploy succeeds, auth gating works, debug route 404s, AI features run on prod.
Add auth + rate limiting to AI API routes | Security | High | 2-4 hrs | Claude | Supabase restored | 0 of 13 AI routes check auth today — anyone could burn Anthropic credits on prod. Add session check + per-user rate limit.
Migrate app data from localStorage to Supabase | Backend | High | 1-2 days | Claude | Supabase restored | Scores, tracker, interview sessions currently save per-browser only. Schema tables already exist; wire reads/writes + auth-scoped queries. Biggest engineering task left.
Configure Stripe live products & keys | Payments | Medium | 1 hr | Nassim + Claude | Stripe account | Create £19.99/mo price in Stripe dashboard; set 4 env vars (secret key, publishable key, webhook secret, price ID); register webhook endpoint.
Wire Full Process Exam to live AI | AI module | Medium | 0.5-1 day | Claude | — | Stage scores are hard-coded demo values; should call the existing AI routes per stage before selling Premium.
Replace placeholder testimonials & claims | Legal/Content | Medium | 1 hr | Nassim | — | Landing shows invented testimonials ('Now at Deloitte/Goldman/McKinsey') and university trust bar. Misleading-advertising risk if launched publicly — replace with real quotes or reframe as illustrative.
Email notifications (verification, reminders) | Backend | Low | 0.5 day | Claude | Supabase restored | Supabase handles auth emails natively; deadline-reminder emails need a provider (e.g. Resend) — optional for launch.
ESLint cleanup (103 legacy errors) | Quality | Low | 0.5 day | Claude | — | Code-quality only (no-explicit-any, unused vars, unescaped entities). No functional impact.
Custom domain | DevOps | Low | 30 min | Nassim | Domain purchase | Optional: point e.g. gradprocess.ai at Vercel; update NEXT_PUBLIC_APP_URL + Supabase site URL.

## Blockers & Risks
Blocker / Risk | Type | Severity | Status | Impact if unresolved | Mitigation / action | Owner
Supabase project deleted | Blocker | Critical | Active | No signup, login, or saved data in ANY environment. App runs on localStorage + dev auth bypass only. | Create new project, run corrected schema.sql, update keys everywhere. ~20 min total. | Nassim
GitHub push authentication failing | Blocker | Critical | Active | Audit fixes (incl. removal of the live API-key leak) cannot reach production. | Personal access token (classic) with 'repo' scope, or install GitHub CLI and 'gh auth login'. | Nassim
API-key prefix publicly exposed on prod | Security | High | Active | Live /api/debug leaks Anthropic key prefix + env metadata until the push deploys; key partially fingerprinted. | Push fixes (deletes route), then rotate the Anthropic key. | Nassim
AI endpoints publicly callable | Security | High | Active | Anyone can call the 13 AI routes on prod without an account → unbounded Anthropic API bill. | Add Supabase session check + rate limiting to AI routes once Supabase is restored (task queued). | Claude
Deploy sequencing: auth gate vs dead Supabase | Dependency | High | Known | Pushing now activates login-gating with a dead login → protected pages unusable until Supabase exists. | Accepted trade-off (leak removal first). Do Supabase setup immediately after push. | Both
User data lives in localStorage | Product | High | Known | Progress lost on browser clear / not synced across devices; can't honour paid accounts properly. | Supabase persistence migration (1-2 days, queued behind infrastructure). | Claude
Supabase free tier auto-pauses | Ops | Medium | Future | This is likely how the original project died — free projects pause after ~1 week inactivity, then get deleted. | Upgrade to paid tier before launch, or set a scheduled keep-alive ping. | Nassim
Stripe not configured | Revenue | Medium | Active | Billing UI renders but checkout 500s — cannot take payment. | 1-hour setup task once ready to monetise (keys + price + webhook endpoint). | Both
Fabricated testimonials on landing page | Legal | Medium | Active | Invented named testimonials + university logos = misleading-advertising exposure (UK CAP code) at public launch. | Replace with real quotes, or clearly mark as illustrative before marketing push. | Nassim
Anthropic API costs at scale | Cost | Medium | Future | Every module hits Claude; heavy free users could outspend revenue. | Rate limits per plan tier; cache common outputs; monitor console.anthropic.com usage alerts. | Both
No error monitoring in production | Ops | Low | Future | Prod failures invisible until users complain. | Add Sentry (or Vercel log drains + alerts) post-launch. | Claude
npm audit: 3 transitive vulns in Next.js tooling | Security | Low | Known | Build-time postcss chain; not exploitable via normal app usage. | Take the next Next.js patch release when available. | Claude